## README
Team Name | The Hooplas
Last Update | 2018-11-02
Author(s) | Patrick Porter, Harnoor Singh, Rotem Werner, Antonio Martinez, Yichao Chen
Email | pport004@ucr.edu, hsing013@ucr.edu, rwern002@ucr.edu, amart108@ucr.edu, ychen177@ucr.edu
Description | Atlas: A word game
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
7 | Create Account | As an unregistered customer who is insterested in the app, I want to register an account so that I can login the app | 5 | 2
1 | Login/Logout | As a registered user, I want to login my account with user name and password, and logout my account to end the session | 2 | 2
2 | Friend List | As a user, I want to add a person into my contacts so that I can connect with my friends and also request to have a match against them | 4 | 3
4 | Pass & Play | As a user, I want to be able to play the game with other people without having to play other people online. | 5 | 4
3 | Leader Board | As a user, I want to want to see who has the largest number of victories and where I am in the overall standing | 3 | 3
6 | Setting | As a user I want to be able to log out of my account once I am signed into the account along with being able to reread the rules and more | 2 | 3
5 | Notification | As a user, I want to receive notification when I get messages from someone | 1 | 3
8 | Multiplayer | As a user, I want to have matches with people online whether they are or are not on my friends list | 7 | 1
9 | AI Bot | As a user,Can play against an AI with levels of difficulty of: Easy, Medium and Hard | 5 | 3
10 | Game Category | As a user, I want to make my current match more interesting by making it more unique or difficult for all of those involved. | 5 | 4
| Total |  | 35

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Create Account (Harnoor Singh) (Rotem Werner)
Task2: Multiplayer(Harnoor Singh(PartrickPorter)
Task 3: Actual Game Working (Harnoor Singh) (Patrick Porter)
Task 4: Cleanup Text File (Harnoor Singh)
Task5: LeaderBoard(Patrick Porter)(AntonioMartinez)
Task6: Basic SQlite Integration (Harnoor Singh)
Task 7: Advance SQlite Interation(HarnoorSingh)
Task 8: Create Notificaition Tab(Yichao Chen)(Antonio Martinez)
Task 9: Setting(Antonio Martinez)
Task10: Friend List(Rotem Werner)(HarnoorSingh)
Task 11: Pass & Play(Rotem Werner)(Yichao Chen)
Task12: AI Bot (Antonio Martinez)
Task 13: Log in after disconnect (Harnoor Singh)
Task 14: Input checker (Rotem Werner)(Harnoor Singh)
Task 15: Add Friends(Rotem Werner)(Patrick Porter)
Task 16: Create XML files for all screens(Everyone)
Task 16: Create Game Category(Harnoor Singh)

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Harnoor Singh
1 | Harnoor Singh | Task 3: Actual Game Working (Harnoor Singh) (Patrick Porter)
Task 4: Cleanup Text File (Harnoor Singh)
Task 1: Create Account (Harnoor Singh) (Rotem Werner)
Task2: Multiplayer(Harnoor Singh(PartrickPorter)
Task5: LeaderBoard(Patrick Porter)(AntonioMartinez)
Task6: Basic SQlite Integration (Harnoor Singh)
Task 7: Advance SQlite Interation(HarnoorSingh)
Task 9: Setting(Antonio Martinez)
Task10: Friend List(Rotem Werner)(HarnoorSingh)
2 | Patrick Porter | Task 11: Pass & Play(Rotem Werner)(Yichao Chen)
Task 13: Log in after disconnect (Harnoor Singh)
Task 14: Input checker (Rotem Werner)(Harnoor Singh)
Task 15: Add Friends(Rotem Werner)(Patrick Porter)
Task 16: Create XML files for all screens(Everyone)

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 0 | 0 | 35 | 35
1 | 35 | 0 | 0 | 35 | 30.625
2 | 35 | 2 | 2 | 33 | 26.25
3 | 35 | 16 | 18 | 17 | 21.875
4 | 39 | 11 | 29 | 6 | 17.5
5 |  |  |  |  | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0